## Rate
Role | USD / HR
Statistician | 30
Sr. Statistician | 40
Stats. Prog. | 25
Sr. Stats. Prog. | 33

## Total efforts
Complexity |  | Low / Simple |  |  | Medium / Standard |  |  | Complex
Role | Activities | Total Efforts in hours | Total Efforts in Days | Total Rate in USD | Total Efforts in hours | Total Efforts in Days | Total Rate in USD | Total Efforts in hours | Total Efforts in Days | Total Rate in USD
SAP | M3,M6 and M7 | 116 | 14.5 | 3517 | 176 | 22 | 5333 | 210 | 26.25 | 6370
| Programming specifications | 183.25 | 22.9062 | 5469 | 291.75 | 36.4688 | 8713 | 366.5 | 45.8125 | 10938
Only Programming and validation with review and no specifications development | SDTM dataset | 196.375 | 24.5469 | 5785.5 | 286.125 | 35.7656 | 8423.5 | 392.75 | 49.0938 | 11571
| ADaM dataset | 253.375 | 31.6719 | 7705.5 | 429.125 | 53.6406 | 13043.5 | 506.75 | 63.3438 | 15411
Programming and validation of datasets with review with specifications development | SDTM dataset | 288 | 36 | 8520 | 432 | 54 | 12780 | 576 | 72 | 17040
| ADaM dataset | 345 | 43.125 | 10440 | 575 | 71.875 | 17400 | 690 | 86.25 | 20880
Programming and validation with review | TLFs | 523 | 65.375 | 14781.5 | 803 | 100.375 | 22686 | 987.5 | 123.4375 | 27884.5
| Intext tables | 64 | 8 | 1863.5 | 128 | 16 | 3727 | 192 | 24 | 5590.5
Submission package | SDTM eSub Package | 194.4 | 24.3 | 5384 | 243 | 30.375 | 6730 | 303.75 | 37.9688 | 8412.5
| ADaM eSub Package | 150.4 | 18.8 | 4196.8 | 188 | 23.5 | 5246 | 235 | 29.375 | 6557.5
Project management | Cost for the role of a TP | 43.5 | 5.4375 | 1435.5 | 44.037 | 5.5046 | 1453.2222 | 52.6296 | 6.5787 | 1736.7778
SAP (Statistical Analysis Plan including mock shells and Specification development including SDTM mapping and PDS) | Total | 299.25 | 37.4062 | 8986 | 467.75 | 58.4688 | 14046 | 576.5 | 72.0625 | 17308
Programming of SDTM, ADaM and TLF and intext with validation and review without specifications development | Total | 1036.75 | 129.5938 | 30136 | 1646.25 | 205.7812 | 47880 | 2079 | 259.875 | 60457
E-submission | Total | 344.8 | 43.1 | 9580.8 | 431 | 53.875 | 11976 | 538.75 | 67.3438 | 14970
DMC | Total | 267.2 | 33.4 | 8972.4 | 422.8 | 52.85 | 14204.7 | 531.1 | 66.3875 | 17826.85
Interim analysis | Total | 400.8 | 50.1 | 13458.6 | 634.2 | 79.275 | 21307.05 | 796.65 | 99.5812 | 26740.275
Interim analysis (IS&IP) | Total | 100.2 | 12.525 | 3364.65 | 158.55 | 19.8188 | 5326.7625 | 199.1625 | 24.8953 | 6685.0688
SAP amendments (1) | Total | 17.4 | 2.175 | 611.25 | 26.4 | 3.3 | 926.7 | 31.5 | 3.9375 | 1107.15
Overall efforts including all the totals | Total | 2509.9 | 308.3 | 76545.2 | 3830.987 | 473.3688 | 117120.4347 | 4805.2921 | 594.0828 | 146831.1215
Overall study effort excluding IS&IP and SAP amendments | Total | 2392.3 | 293.6 | 72569.3 | 3646.037 | 450.25 | 110866.9722 | 4574.6296 | 565.25 | 139038.9028
Overall study effort excluding IS&IP and SAP amendments and e-submission and DMC only 1 IA included | Total | 1780.3 | 217.1 | 54016.1 | 2792.237 | 343.525 | 84686.2722 | 3504.7796 | 431.5188 | 106242.0528
Overall study effort excluding IS&IP and SAP amendments and e-submission and DMC and IA | Total | 1379.5 | -100.375 | 40557.5 | 2158.037 | 264.25 | 63379.2222 | 2708.1296 | 331.9375 | 79501.7778

## For presentation
Domain | Activity | Role | Low complexity |  | Medium |  | Complex
|  |  | Efforts | Cost | Efforts | Cost | Efforts | Cost
BSP | Cost per RAP SAP including Mock shells | Statistician | 65 | 1950 | 99 | 2970 | 118 | 3540
|  | Sr. Statistician | 12 | 480 | 18 | 720 | 22 | 880
|  | Stats. Prog. | 25 | 625 | 38 | 950 | 45 | 1125
|  | Sr. Stats. Prog. | 14 | 462 | 21 | 693 | 25 | 825
|  | Total | 116 | 3517 | 176 | 5333 | 210 | 6370
| Cost for Programming specifications | Statistician | 23.5 | 705 | 36.5 | 1095 | 47 | 1410
|  | Sr. Statistician | 9.75 | 390 | 15.25 | 610 | 19.5 | 780
|  | Stats. Prog. | 72 | 1800 | 114 | 2850 | 144 | 3600
|  | Sr. Stats. Prog. | 78 | 2574 | 126 | 4158 | 156 | 5148
|  | Total | 183.25 | 5469 | 291.75 | 8713 | 366.5 | 10938
| Cost for SDTM and ADaM creation | Statistician | 70.5 | 2115 | 109.5 | 3285 | 141 | 4230
|  | Sr. Statistician | 29.25 | 1170 | 45.75 | 1830 | 58.5 | 2340
|  | Stats. Prog. | 168 | 4200 | 266 | 6650 | 336 | 8400
|  | Sr. Stats. Prog. | 182 | 6006 | 294 | 9702 | 364 | 12012
|  | Total | 449.75 | 13491 | 715.25 | 21467 | 899.5 | 26982
| Cost for TLF with intext tables | Statistician | 109 | 3270 | 170 | 5100 | 207.75 | 6232.5
|  | Sr. Statistician | 31 | 1240 | 52 | 2080 | 71.25 | 2850
|  | Stats. Prog. | 327 | 8175 | 520.5 | 13012.5 | 665.5 | 16637.5
|  | Sr. Stats. Prog. | 120 | 3960 | 188.5 | 6220.5 | 235 | 7755
|  | Total | 587 | 16645 | 931 | 26413 | 1179.5 | 33475
| Total cost of study including TP role excluding DSMB and Interim Analysis | Total | 1379.5 | 40557.5 | 2158.037 | 63379.2222 | 2708.1296 | 79501.7778
| Cost per DSMB Analysis | Statistician | 53.6 | 1876 | 83 | 2905 | 102.75 | 3596.25
|  | Sr. Statistician | 16.4 | 787.2 | 26.2 | 1257.6 | 34.25 | 1644
|  | Stats. Prog. | 118.4 | 3078.4 | 187.7 | 4880.2 | 238.1 | 6190.6
|  | Sr. Stats. Prog. | 78.8 | 3230.8 | 125.9 | 5161.9 | 156 | 6396
|  | Total | 267.2 | 8972.4 | 422.8 | 14204.7 | 531.1 | 17826.85
| Interim analysis | Statistician | 80.4 | 2814 | 124.5 | 4357.5 | 154.125 | 5394.375
|  | Sr. Statistician | 24.6 | 1180.8 | 39.3 | 1886.4 | 51.375 | 2466
|  | Stats. Prog. | 177.6 | 4617.6 | 281.55 | 7320.3 | 357.15 | 9285.9
|  | Sr. Stats. Prog. | 118.2 | 4846.2 | 188.85 | 7742.85 | 234 | 9594
|  | Total | 400.8 | 13458.6 | 634.2 | 21307.05 | 796.65 | 26740.275
| Total cost of study including TP 1 DSMB and 1 Interim Analysis | Total | 2047.5 | 62988.5 | 3215.037 | 98890.9722 | 4035.8796 | 124068.9028

## Efforts with Complexity
C&R | Creation and Review during development
C&V&spec | Creation & Validation & specification development
C&V | Creation & Validation
Efforts calculations with details
Deliverables |  |  |  | no. of units | Amendment
M3- Statistical methodology |  |  |  | 1 | 1
M6- intext tables |  |  |  | 1 | 1
M7- post text tables |  |  |  | 1 | 1
M8- SDTM & ADaM Analysis dataset specifications |  |  |  | Specification development included in the efforts for SDTM ad ADaM dataset activity. E-submission for SDTM and ADaM displayed seperately
Low complexity | [5 empty] | Medium complexity | [5 empty] | High complexity
Deliverables | no. of units | unique | repeat | Intext |  | Deliverables | no. of units | unique | repeat | Intext |  | Deliverables | no. of units | unique | repeat | Intext
SDTM dataset | 20 |  |  |  |  | SDTM dataset | 30 |  |  |  |  | SDTM dataset | 40
ADaM dataset | 15 |  |  |  |  | ADaM dataset | 25 |  |  |  |  | ADaM dataset | 30
Tables | 60 | 42 | 18 | 6 |  | Tables | 90 | 67 | 23 | 12 |  | Tables | 105 | 89 | 16 | 18
Listings | 30 | 21 | 9 | 3 |  | Listings | 45 | 34 | 11 | 6 |  | Listings | 52.5 | 44.5 | 8 | 9
Graphs | 10 | 7 | 3 | 1 |  | Graphs | 15 | 11 | 4 | 2 |  | Graphs | 17.5 | 14.5 | 3 | 3
Total Efforts = Planning + Execution
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | Very High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
M3,M6 and M7 | C&R | Statistician | 65 | 8.125 | 1950 |  | 99 | 12.375 | 2970 |  | 118 | 14.75 | 3540
M3,M6 and M7 | C&R | Sr. Statistician | 12 | 1.5 | 480 |  | 18 | 2.25 | 720 |  | 22 | 2.75 | 880
M3,M6 and M7 | C&R | Stats. Prog. | 25 | 3.125 | 625 |  | 38 | 4.75 | 950 |  | 45 | 5.625 | 1125
M3,M6 and M7 | C&R | Sr. Stats. Prog. | 14 | 1.75 | 462 |  | 21 | 2.625 | 693 |  | 25 | 3.125 | 825
M3,M6 and M7 | C&R | Total | 116 | 14.5 | 3517 |  | 176 | 22 | 5333 |  | 210 | 26.25 | 6370
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
SDTM dataset | C&V&spec | Statistician | 64 | 8 | 1920 |  | 96 | 12 | 2880 |  | 128 | 16 | 3840
SDTM dataset | C&V&spec | Sr. Statistician | 24 | 3 | 960 |  | 36 | 4.5 | 1440 |  | 48 | 6 | 1920
SDTM dataset | C&V&spec | Stats. Prog. | 120 | 15 | 3000 |  | 180 | 22.5 | 4500 |  | 240 | 30 | 6000
SDTM dataset | C&V&spec | Sr. Stats. Prog. | 80 | 10 | 2640 |  | 120 | 15 | 3960 |  | 160 | 20 | 5280
SDTM dataset | C&V&spec | Total | 288 | 36 | 8520 |  | 432 | 54 | 12780 |  | 576 | 72 | 17040
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
ADaM dataset | C&V&spec | Statistician | 30 | 3.75 | 900 |  | 50 | 6.25 | 1500 |  | 60 | 7.5 | 1800
ADaM dataset | C&V&spec | Sr. Statistician | 15 | 1.875 | 600 |  | 25 | 3.125 | 1000 |  | 30 | 3.75 | 1200
ADaM dataset | C&V&spec | Stats. Prog. | 120 | 15 | 3000 |  | 200 | 25 | 5000 |  | 240 | 30 | 6000
ADaM dataset | C&V&spec | Sr. Stats. Prog. | 180 | 22.5 | 5940 |  | 300 | 37.5 | 9900 |  | 360 | 45 | 11880
ADaM dataset | C&V&spec | Total | 345 | 43.125 | 10440 |  | 575 | 71.875 | 17400 |  | 690 | 86.25 | 20880
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
TLFs | C&V&Review | Statistician | 95 | 11.875 | 2850 |  | 142 | 17.75 | 4260 |  | 165.75 | 20.7188 | 4972.5
TLFs | C&V&Review | Sr. Statistician | 24.5 | 3.0625 | 980 |  | 39 | 4.875 | 1560 |  | 51.75 | 6.4688 | 2070
TLFs | C&V&Review | Stats. Prog. | 295.5 | 36.9375 | 7387.5 |  | 457.5 | 57.1875 | 11437.5 |  | 571 | 71.375 | 14275
TLFs | C&V&Review | Sr. Stats. Prog. | 108 | 13.5 | 3564 |  | 164.5 | 20.5625 | 5428.5 |  | 199 | 24.875 | 6567
TLFs | C&V&Review | Total | 523 | 65.375 | 14781.5 |  | 803 | 100.375 | 22686 |  | 987.5 | 123.4375 | 27884.5
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
Intext tables | C&V&Review | Statistician | 14 | 1.75 | 420 |  | 28 | 3.5 | 840 |  | 42 | 5.25 | 1260
Intext tables | C&V&Review | Sr. Statistician | 6.5 | 0.8125 | 260 |  | 13 | 1.625 | 520 |  | 19.5 | 2.4375 | 780
Intext tables | C&V&Review | Stats. Prog. | 31.5 | 3.9375 | 787.5 |  | 63 | 7.875 | 1575 |  | 94.5 | 11.8125 | 2362.5
Intext tables | C&V&Review | Sr. Stats. Prog. | 12 | 1.5 | 396 |  | 24 | 3 | 792 |  | 36 | 4.5 | 1188
Intext tables | C&V&Review | Total | 64 | 8 | 1863.5 |  | 128 | 16 | 3727 |  | 192 | 24 | 5590.5
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
SDTM eSub Package | C&V | Statistician | 2.4 | 0.3 | 72 |  | 3 | 0.375 | 90 |  | 3.75 | 0.46875 | 112.5
SDTM eSub Package | C&V | Sr. Statistician | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
SDTM eSub Package | C&V | Stats. Prog. | 128 | 16 | 3200 |  | 160 | 20 | 4000 |  | 200 | 25 | 5000
SDTM eSub Package | C&V | Sr. Stats. Prog. | 64 | 8 | 2112 |  | 80 | 10 | 2640 |  | 100 | 12.5 | 3300
SDTM eSub Package | C&V | Total | 194.4 | 24.3 | 5384 |  | 243 | 30.375 | 6730 |  | 303.75 | 37.9688 | 8412.5
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
ADaM eSub Package | C&V | Statistician | 8 | 1 | 240 |  | 10 | 1.25 | 300 |  | 12.5 | 1.5625 | 375
ADaM eSub Package | C&V | Sr. Statistician | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
ADaM eSub Package | C&V | Stats. Prog. | 92.8 | 11.6 | 2320 |  | 116 | 14.5 | 2900 |  | 145 | 18.125 | 3625
ADaM eSub Package | C&V | Sr. Stats. Prog. | 49.6 | 6.2 | 1636.8 |  | 62 | 7.75 | 2046 |  | 77.5 | 9.6875 | 2557.5
ADaM eSub Package | C&V | Total | 150.4 | 18.8 | 4196.8 |  | 188 | 23.5 | 5246 |  | 235 | 29.375 | 6557.5
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
Statistical programming | C&V | Statistician | 203 | 25.375 | 6090 |  | 316 | 39.5 | 9480 |  | 395.75 | 49.4688 | 11872.5
Statistical programming | C&V | Sr. Statistician | 70 | 8.75 | 2800 |  | 113 | 14.125 | 4520 |  | 149.25 | 18.6562 | 5970
Statistical programming | C&V | Stats. Prog. | 567 | 70.875 | 14175 |  | 900.5 | 112.5625 | 22512.5 |  | 1145.5 | 143.1875 | 28637.5
Statistical programming | C&V | Sr. Stats. Prog. | 380 | 47.5 | 12540 |  | 608.5 | 76.0625 | 20080.5 |  | 755 | 94.375 | 24915
Statistical programming | C&V | Total | 1220 | 152.5 | 35605 |  | 1938 | 242.25 | 56593 |  | 2445.5 | 305.6875 | 71395
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
eSub Package | C&V | Statistician | 10.4 | 1.3 | 312 |  | 13 | 1.625 | 390 |  | 16.25 | 2.0312 | 487.5
eSub Package | C&V | Sr. Statistician | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
eSub Package | C&V | Stats. Prog. | 220.8 | 27.6 | 5520 |  | 276 | 34.5 | 6900 |  | 345 | 43.125 | 8625
eSub Package | C&V | Sr. Stats. Prog. | 113.6 | 14.2 | 3748.8 |  | 142 | 17.75 | 4686 |  | 177.5 | 22.1875 | 5857.5
eSub Package | C&V | Total | 344.8 | 43.1 | 9580.8 |  | 431 | 53.875 | 11976 |  | 538.75 | 67.3438 | 14970
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  |  | 5180.6 | 647.575
Total study cost | C&V | Statistician | 278.4 | 34.8 | 8352 |  | 428 | 53.5 | 12840 |  | 530 | 66.25 | 15900
Total study cost | C&V | Sr. Statistician | 82 | 10.25 | 3280 |  | 131 | 16.375 | 5240 |  | 171.25 | 21.4062 | 6850
Total study cost | C&V | Stats. Prog. | 812.8 | 101.6 | 20320 |  | 1214.5 | 151.8125 | 30362.5 |  | 1535.5 | 191.9375 | 38387.5 |  |  |  |  | 160000 | 67265
Total study cost | C&V | Sr. Stats. Prog. | 507.6 | 63.45 | 16750.8 |  | 771.5 | 96.4375 | 25459.5 |  | 957.5 | 119.6875 | 31597.5
Total study cost | C&V | Total | 1680.8 | 210.1 | 48702.8 |  | 2545 | 318.125 | 73902 |  | 3194.25 | 399.2812 | 92735 |  | dryrun | 1916.55 | 239.5687 | 55641
[15 empty] | final run | 958.275 | 119.7844 | 27820.5
[15 empty] | dryrun -2 | 319.425 | 39.9281 | 9273.5
Cost for the role of a TP | Role of TP | Sr. Stats. Prog. | 43.5 | 5.4375 | 1435.5 |  | 44.037 | 5.5046 | 1453.2222 |  | 52.6296 | 6.5787 | 1736.7778 |  | final run | 1986.35 | 248.2938 | 67265
Total study cost including TP Role | TP+study | Total | 1724.3 | 215.5375 | 50138.3 |  | 2589.037 | 323.6296 | 75355.2222 |  | 3246.8796 | 405.86 | 94471.7778
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
Programming specification | Spec development & review | Statistician | 23.5 | 2.9375 | 705 |  | 36.5 | 4.5625 | 1095 |  | 47 | 5.875 | 1410
Programming specification | Spec development & review | Sr. Statistician | 9.75 | 1.2188 | 390 |  | 15.25 | 1.9062 | 610 |  | 19.5 | 2.4375 | 780
Programming specification | Spec development & review | Stats. Prog. | 72 | 9 | 1800 |  | 114 | 14.25 | 2850 |  | 144 | 18 | 3600
Programming specification | Spec development & review | Sr. Stats. Prog. | 78 | 9.75 | 2574 |  | 126 | 15.75 | 4158 |  | 156 | 19.5 | 5148
Programming specification | Spec development & review | Total | 183.25 | 22.9062 | 5469 |  | 291.75 | 36.4688 | 8713 |  | 366.5 | 45.8125 | 10938
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
DMC | Programming + programming spec +Review | Statistician | 53.6 | 6.7 | 1876 |  | 83 | 10.375 | 2905 |  | 102.75 | 12.8438 | 3596.25
DMC | Programming + programming spec +Review | Sr. Statistician | 16.4 | 2.05 | 787.2 |  | 26.2 | 3.275 | 1257.6 |  | 34.25 | 4.2812 | 1644
DMC | Programming + programming spec +Review | Stats. Prog. | 118.4 | 14.8 | 3078.4 |  | 187.7 | 23.4625 | 4880.2 |  | 238.1 | 29.7625 | 6190.6
DMC | Programming + programming spec +Review | Sr. Stats. Prog. | 78.8 | 9.85 | 3230.8 |  | 125.9 | 15.7375 | 5161.9 |  | 156 | 19.5 | 6396
DMC | Programming + programming spec +Review | Total | 267.2 | 33.4 | 8972.4 |  | 422.8 | 52.85 | 14204.7 |  | 531.1 | 66.3875 | 17826.85
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
IA | Programming + programming spec +Review | Statistician | 80.4 | 10.05 | 2814 |  | 124.5 | 15.5625 | 4357.5 |  | 154.125 | 19.2656 | 5394.375
IA | Programming + programming spec +Review | Sr. Statistician | 24.6 | 3.075 | 1180.8 |  | 39.3 | 4.9125 | 1886.4 |  | 51.375 | 6.4219 | 2466
IA | Programming + programming spec +Review | Stats. Prog. | 177.6 | 22.2 | 4617.6 |  | 281.55 | 35.1938 | 7320.3 |  | 357.15 | 44.6437 | 9285.9
IA | Programming + programming spec +Review | Sr. Stats. Prog. | 118.2 | 14.775 | 4846.2 |  | 188.85 | 23.6062 | 7742.85 |  | 234 | 29.25 | 9594
IA | Programming + programming spec +Review | Total | 400.8 | 50.1 | 13458.6 |  | 634.2 | 79.275 | 21307.05 |  | 796.65 | 99.5812 | 26740.275
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
IA | Independent stat and programming | Statistician | 20.1 | 2.5125 | 703.5 |  | 31.125 | 3.8906 | 1089.375 |  | 38.5312 | 4.8164 | 1348.5938
IA | Independent stat and programming | Sr. Statistician | 6.15 | 0.76875 | 295.2 |  | 9.825 | 1.2281 | 471.6 |  | 12.8438 | 1.6055 | 616.5
IA | Independent stat and programming | Stats. Prog. | 44.4 | 5.55 | 1154.4 |  | 70.3875 | 8.7984 | 1830.075 |  | 89.2875 | 11.1609 | 2321.475
IA | Independent stat and programming | Sr. Stats. Prog. | 29.55 | 3.6937 | 1211.55 |  | 47.2125 | 5.9016 | 1935.7125 |  | 58.5 | 7.3125 | 2398.5
IA | Independent stat and programming | Total | 100.2 | 12.525 | 3364.65 |  | 158.55 | 19.8188 | 5326.7625 |  | 199.1625 | 24.8953 | 6685.0688
Activity | Sub Activity | Role | Low complexity |  |  |  | Medium complexity |  |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost |  | Efforts in hours | Efforts in days | Cost
SAP amendment | C&R | Statistician | 9.75 | 1.2188 | 341.25 |  | 14.85 | 1.8562 | 519.75 |  | 17.7 | 2.2125 | 619.5
SAP amendment | C&R | Sr. Statistician | 1.8 | 0.225 | 86.4 |  | 2.7 | 0.3375 | 129.6 |  | 3.3 | 0.4125 | 158.4
SAP amendment | C&R | Stats. Prog. | 3.75 | 0.46875 | 97.5 |  | 5.7 | 0.7125 | 148.2 |  | 6.75 | 0.84375 | 175.5
SAP amendment | C&R | Sr. Stats. Prog. | 2.1 | 0.2625 | 86.1 |  | 3.15 | 0.39375 | 129.15 |  | 3.75 | 0.46875 | 153.75
SAP amendment | C&R | Total | 17.4 | 2.175 | 611.25 |  | 26.4 | 3.3 | 926.7 |  | 31.5 | 3.9375 | 1107.15

## Responsibility of TP
Role of a TP | hours | units | total units for low complexity | Total units for medium complexity | Total units for high complexity
1) Programming team management, Timeline management , negotiation with the team | 2 | 5 | 10 | 15.1852 | 18.1481
2) Study programming team meetings with DM and stat | 1 | 5 | 5 | 7.5926 | 9.0741
3) attend RAP review meetings (M3, M7 ) | 1 | 2 | 2 | 3.037 | 3.6296
4) Attend dryrun review meetings | 2 | 2 | 4 | 6.0741 | 7.2593
5) Attend Trial team meetings as required | 1 | 5 | 5 | 7.5926 | 9.0741
6) attend data quality review meeting as applicable | 1 | 3 | 3 | 4.5556 | 5.4444
7) Review of PDS, and output review (accounted for in SDTM and ADaM creation)
| 8 | 22 | 29 | 44.037 | 52.6296

## outputs
| TLF | Table | Listing | Figure |  | multiplier | Repeat | Intext TLF | Table | Listing | Figure |  | multiplier
Low | 100 | 6 | 3 | 1 | Ratio | 10 |  | 10 | 6 | 3 | 1 | Ratio | 1
|  | 60 | 30 | 10 | Actual number |  |  |  | 6 | 3 | 1 | Actual number
| Repeat | 18 | 9 | 3 |  |  | 30%
| unique | 42 | 21 | 7
Medium | 150 | 6 | 3 | 1 | Ratio | 15 |  | 20 | 6 | 3 | 1 | Ratio | 2
|  | 90 | 45 | 15 | Actual number |  |  |  | 12 | 6 | 2 | Actual number
| Repeat | 23 | 11 | 4 |  |  | 25%
| unique | 67 | 34 | 11
Medium | 175 | 6 | 3 | 1 | Ratio | 17.5 |  | 30 | 6 | 3 | 1 | Ratio | 3
|  | 105 | 52.5 | 17.5 | Actual number |  |  |  | 18 | 9 | 3 | Actual number
| Repeat | 16 | 8 | 3 |  |  | 15%
| unique | 89 | 44.5 | 14.5
Only highlighted values to be updated, rest is automatically calculated.

## low
Activity | Sub Activity | Role | Hours / Unit | No. of Units | Efforts | Cost
SAP and Mock shells | Creation | Statistician | 64 | 1 | 64 | 1920
SAP and Mock shells | Creation | Sr. Statistician | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Stats. Prog. | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Sr. Stats. Prog. | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Total | 64 | 1 | 64 | 1920
SAP and Mock shells
SAP and Mock shells | Review | Statistician | 1 | 1 | 1 | 30
SAP and Mock shells | Review | Sr. Statistician | 12 | 1 | 12 | 480
SAP and Mock shells | Review | Stats. Prog. | 25 | 1 | 25 | 625
SAP and Mock shells | Review | Sr. Stats. Prog. | 14 | 1 | 14 | 462
SAP and Mock shells | Review | Total | 52 | 1 | 52 | 1597
SDTM | Creation | Statistician | 0 | 20 | 0 | 0
SDTM | Creation | Sr. Statistician | 0 | 20 | 0 | 0
SDTM | Creation | Stats. Prog. | 6 | 20 | 120 | 3000
SDTM | Creation | Sr. Stats. Prog. | 0 | 20 | 0 | 0
SDTM | Creation | Total | 6 | 20 | 120 | 3000
SDTM
SDTM | Validation | Statistician | 3.2 | 20 | 64 | 1920
SDTM | Validation | Sr. Statistician | 1.2 | 20 | 24 | 960
SDTM | Validation | Stats. Prog. | 0 | 20 | 0 | 0
SDTM | Validation | Sr. Stats. Prog. | 4 | 20 | 80 | 2640
SDTM | Validation | Total | 8.4 | 20 | 168 | 5520
ADaM | Creation | Statistician | 1 | 15 | 15 | 450
ADaM | Creation | Sr. Statistician | 0 | 15 | 0 | 0
ADaM | Creation | Stats. Prog. | 8 | 15 | 120 | 3000
ADaM | Creation | Sr. Stats. Prog. | 0 | 15 | 0 | 0
ADaM | Creation | Total | 9 | 15 | 135 | 3450
ADaM
ADaM | Validation | Statistician | 1 | 15 | 15 | 450
ADaM | Validation | Sr. Statistician | 1 | 15 | 15 | 600
ADaM | Validation | Stats. Prog. | 0 | 15 | 0 | 0
ADaM | Validation | Sr. Stats. Prog. | 12 | 15 | 180 | 5940
ADaM | Validation | Total | 14 | 15 | 210 | 6990
Tables - Unique | Creation | Statistician | 0.5 | 42 | 21 | 630
Tables - Unique | Creation | Sr. Statistician | 0 | 42 | 0 | 0
Tables - Unique | Creation | Stats. Prog. | 4 | 42 | 168 | 4200
Tables - Unique | Creation | Sr. Stats. Prog. | 0 | 42 | 0 | 0
Tables - Unique | Creation | Total | 4.5 | 42 | 189 | 4830
Tables - Unique
Tables - Unique | Validation | Statistician | 0.5 | 42 | 21 | 630
Tables - Unique | Validation | Sr. Statistician | 0.5 | 42 | 21 | 840
Tables - Unique | Validation | Stats. Prog. | 0 | 42 | 0 | 0
Tables - Unique | Validation | Sr. Stats. Prog. | 1.5 | 42 | 63 | 2079
Tables - Unique | Validation | Total | 2.5 | 42 | 105 | 3549
Tables - Repeat | Creation | Statistician | 0.5 | 18 | 9 | 270
Tables - Repeat | Creation | Sr. Statistician | 0 | 18 | 0 | 0
Tables - Repeat | Creation | Stats. Prog. | 2 | 18 | 36 | 900
Tables - Repeat | Creation | Sr. Stats. Prog. | 0 | 18 | 0 | 0
Tables - Repeat | Creation | Total | 2.5 | 18 | 45 | 1170
Tables - Repeat
Tables - Repeat | Validation | Statistician | 0.5 | 18 | 9 | 270
Tables - Repeat | Validation | Sr. Statistician | 0 | 18 | 0 | 0
Tables - Repeat | Validation | Stats. Prog. | 0 | 18 | 0 | 0
Tables - Repeat | Validation | Sr. Stats. Prog. | 1 | 18 | 18 | 594
Tables - Repeat | Validation | Total | 1.5 | 18 | 27 | 864
Listings - Unique | Creation | Statistician | 0 | 21 | 0 | 0
Listings - Unique | Creation | Sr. Statistician | 0 | 21 | 0 | 0
Listings - Unique | Creation | Stats. Prog. | 2 | 21 | 42 | 1050
Listings - Unique | Creation | Sr. Stats. Prog. | 0 | 21 | 0 | 0
Listings - Unique | Creation | Total | 2 | 21 | 42 | 1050
Listings - Unique
Listings - Unique | Validation | Statistician | 0.5 | 21 | 10.5 | 315
Listings - Unique | Validation | Sr. Statistician | 0 | 21 | 0 | 0
Listings - Unique | Validation | Stats. Prog. | 0 | 21 | 0 | 0
Listings - Unique | Validation | Sr. Stats. Prog. | 0.5 | 21 | 10.5 | 346.5
Listings - Unique | Validation | Total | 1 | 21 | 21 | 661.5
Listings - Repeat | Creation | Statistician | 0 | 9 | 0 | 0
Listings - Repeat | Creation | Sr. Statistician | 0 | 9 | 0 | 0
Listings - Repeat | Creation | Stats. Prog. | 0.5 | 9 | 4.5 | 112.5
Listings - Repeat | Creation | Sr. Stats. Prog. | 0 | 9 | 0 | 0
Listings - Repeat | Creation | Total | 0.5 | 9 | 4.5 | 112.5
Listings - Repeat
Listings - Repeat | Validation | Statistician | 1 | 9 | 9 | 270
Listings - Repeat | Validation | Sr. Statistician | 0 | 9 | 0 | 0
Listings - Repeat | Validation | Stats. Prog. | 0 | 9 | 0 | 0
Listings - Repeat | Validation | Sr. Stats. Prog. | 0.5 | 9 | 4.5 | 148.5
Listings - Repeat | Validation | Total | 1.5 | 9 | 13.5 | 418.5
Figuress - Unique | Creation | Statistician | 1 | 7 | 7 | 210
Figuress - Unique | Creation | Sr. Statistician | 0 | 7 | 0 | 0
Figuress - Unique | Creation | Stats. Prog. | 6 | 7 | 42 | 1050
Figuress - Unique | Creation | Sr. Stats. Prog. | 0 | 7 | 0 | 0
Figuress - Unique | Creation | Total | 7 | 7 | 49 | 1260
Figuress - Unique
Figuress - Unique | Validation | Statistician | 1 | 7 | 7 | 210
Figuress - Unique | Validation | Sr. Statistician | 0.5 | 7 | 3.5 | 140
Figuress - Unique | Validation | Stats. Prog. | 0 | 7 | 0 | 0
Figuress - Unique | Validation | Sr. Stats. Prog. | 1.5 | 7 | 10.5 | 346.5
Figuress - Unique | Validation | Total | 3 | 7 | 21 | 696.5
Figures - Repeat | Creation | Statistician | 0 | 3 | 0 | 0
Figures - Repeat | Creation | Sr. Statistician | 0 | 3 | 0 | 0
Figures - Repeat | Creation | Stats. Prog. | 1 | 3 | 3 | 75
Figures - Repeat | Creation | Sr. Stats. Prog. | 0 | 3 | 0 | 0
Figures - Repeat | Creation | Total | 1 | 3 | 3 | 75
Figures - Repeat
Figures - Repeat | Validation | Statistician | 0.5 | 3 | 1.5 | 45
Figures - Repeat | Validation | Sr. Statistician | 0 | 3 | 0 | 0
Figures - Repeat | Validation | Stats. Prog. | 0 | 3 | 0 | 0
Figures - Repeat | Validation | Sr. Stats. Prog. | 0.5 | 3 | 1.5 | 49.5
Figures - Repeat | Validation | Total | 1 | 3 | 3 | 94.5
Tables - Intext | Creation | Statistician | 0.5 | 6 | 3 | 90
Tables - Intext | Creation | Sr. Statistician | 0 | 6 | 0 | 0
Tables - Intext | Creation | Stats. Prog. | 4 | 6 | 24 | 600
Tables - Intext | Creation | Sr. Stats. Prog. | 0 | 6 | 0 | 0
Tables - Intext | Creation | Total | 4.5 | 6 | 27 | 690
Tables - Intext
Tables - Intext | Validation | Statistician | 0.5 | 6 | 3 | 90
Tables - Intext | Validation | Sr. Statistician | 0.5 | 6 | 3 | 120
Tables - Intext | Validation | Stats. Prog. | 0 | 6 | 0 | 0
Tables - Intext | Validation | Sr. Stats. Prog. | 1.5 | 6 | 9 | 297
Tables - Intext | Validation | Total | 2.5 | 6 | 15 | 507
Listings - Intext | Creation | Statistician | 1 | 3 | 3 | 90 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Creation | Sr. Statistician | 0 | 3 | 0 | 0
Listings - Intext | Creation | Stats. Prog. | 0.5 | 3 | 1.5 | 37.5
Listings - Intext | Creation | Sr. Stats. Prog. | 0 | 3 | 0 | 0
Listings - Intext | Creation | Total | 1.5 | 3 | 4.5 | 127.5
Listings - Intext
Listings - Intext | Validation | Statistician | 1 | 3 | 3 | 90 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Validation | Sr. Statistician | 1 | 3 | 3 | 120 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Validation | Stats. Prog. | 0 | 3 | 0 | 0
Listings - Intext | Validation | Sr. Stats. Prog. | 0.5 | 3 | 1.5 | 49.5
Listings - Intext | Validation | Total | 2.5 | 3 | 7.5 | 259.5
Figures - Intext | Creation | Statistician | 1 | 1 | 1 | 30
Figures - Intext | Creation | Sr. Statistician | 0 | 1 | 0 | 0
Figures - Intext | Creation | Stats. Prog. | 6 | 1 | 6 | 150
Figures - Intext | Creation | Sr. Stats. Prog. | 0 | 1 | 0 | 0
Figures - Intext | Creation | Total | 7 | 1 | 7 | 180
Figures - Intext
Figures - Intext | Validation | Statistician | 1 | 1 | 1 | 30
Figures - Intext | Validation | Sr. Statistician | 0.5 | 1 | 0.5 | 20
Figures - Intext | Validation | Stats. Prog. | 0 | 1 | 0 | 0
Figures - Intext | Validation | Sr. Stats. Prog. | 1.5 | 1 | 1.5 | 49.5
Figures - Intext | Validation | Total | 3 | 1 | 3 | 99.5
Total | Creation | Statistician |  |  | 52 | 1560
Total | Creation | Sr. Statistician |  |  | 0 | 0
Total | Creation | Stats. Prog. |  |  | 415.5 | 10387.5
Total | Creation | Sr. Stats. Prog. |  |  | 0 | 0
Total | Creation | Total |  |  | 467.5 | 11947.5
Total |  | Total Check |  |  | 467.5 | 11947.5
Total | Validation | Statistician |  |  | 73 | 2190
Total | Validation | Sr. Statistician |  |  | 39.5 | 1580
Total | Validation | Stats. Prog. |  |  | 0 | 0
Total | Validation | Sr. Stats. Prog. |  |  | 288 | 9504
Total | Validation | Total |  |  | 400.5 | 13274
Total |  | Total Check |  |  | 400.5 | 13274
Grand Total | C&V | Statistician |  |  | 125 | 3750 | 187.5 |  | 62.5
Grand Total | C&V | Sr. Statistician |  |  | 39.5 | 1580 | 59.25 |  | 19.75
Grand Total | C&V | Stats. Prog. |  |  | 415.5 | 10387.5 | 623.25 |  | 207.75
Grand Total | C&V | Sr. Stats. Prog. |  |  | 288 | 9504 | 432 |  | 144
Grand Total | C&V | Total |  |  | 868 | 25221.5 | 1302 |  | 434
Grand Total | C&V | Total Check |  |  | 868 | 25221.5 | 1302 |  | 434
[5 empty] | TLF |  | ADaM
|  | Statistician |  |  | 95 |  | 30
|  | Sr. Statistician |  |  | 24.5 |  | 15
|  | Stats. Prog. |  |  | 295.5 |  | 120
|  | Sr. Stats. Prog. |  |  | 108 |  | 180
Total

## Medium
|  |  |  | Multiplier for unit for SAP |  |  | 1.5185
Activity | Sub Activity | Role | Hours / Unit | No. of Units | Efforts | Cost
SAP and Mock shells | Creation | Statistician | 64 | 1 | 97 | 2910
SAP and Mock shells | Creation | Sr. Statistician | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Stats. Prog. | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Sr. Stats. Prog. | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Total | 64 | 1 | 97 | 2910
SAP and Mock shells
SAP and Mock shells | Review | Statistician | 1 | 1 | 2 | 60
SAP and Mock shells | Review | Sr. Statistician | 12 | 1 | 18 | 720
SAP and Mock shells | Review | Stats. Prog. | 25 | 1 | 38 | 950
SAP and Mock shells | Review | Sr. Stats. Prog. | 14 | 1 | 21 | 693
SAP and Mock shells | Review | Total | 52 | 1 | 79 | 2423
SDTM | Creation | Statistician | 0 | 30 | 0 | 0
SDTM | Creation | Sr. Statistician | 0 | 30 | 0 | 0
SDTM | Creation | Stats. Prog. | 6 | 30 | 180 | 4500
SDTM | Creation | Sr. Stats. Prog. | 0 | 30 | 0 | 0
SDTM | Creation | Total | 6 | 30 | 180 | 4500
SDTM
SDTM | Validation | Statistician | 3.2 | 30 | 96 | 2880
SDTM | Validation | Sr. Statistician | 1.2 | 30 | 36 | 1440
SDTM | Validation | Stats. Prog. | 0 | 30 | 0 | 0
SDTM | Validation | Sr. Stats. Prog. | 4 | 30 | 120 | 3960
SDTM | Validation | Total | 8.4 | 30 | 252 | 8280
ADaM | Creation | Statistician | 1 | 25 | 25 | 750
ADaM | Creation | Sr. Statistician | 0 | 25 | 0 | 0
ADaM | Creation | Stats. Prog. | 8 | 25 | 200 | 5000
ADaM | Creation | Sr. Stats. Prog. | 0 | 25 | 0 | 0
ADaM | Creation | Total | 9 | 25 | 225 | 5750
ADaM
ADaM | Validation | Statistician | 1 | 25 | 25 | 750
ADaM | Validation | Sr. Statistician | 1 | 25 | 25 | 1000
ADaM | Validation | Stats. Prog. | 0 | 25 | 0 | 0
ADaM | Validation | Sr. Stats. Prog. | 12 | 25 | 300 | 9900
ADaM | Validation | Total | 14 | 25 | 350 | 11650
Tables - Unique | Creation | Statistician | 0.5 | 67 | 33.5 | 1005
Tables - Unique | Creation | Sr. Statistician | 0 | 67 | 0 | 0
Tables - Unique | Creation | Stats. Prog. | 4 | 67 | 268 | 6700
Tables - Unique | Creation | Sr. Stats. Prog. | 0 | 67 | 0 | 0
Tables - Unique | Creation | Total | 4.5 | 67 | 301.5 | 7705
Tables - Unique
Tables - Unique | Validation | Statistician | 0.5 | 67 | 33.5 | 1005
Tables - Unique | Validation | Sr. Statistician | 0.5 | 67 | 33.5 | 1340
Tables - Unique | Validation | Stats. Prog. | 0 | 67 | 0 | 0
Tables - Unique | Validation | Sr. Stats. Prog. | 1.5 | 67 | 100.5 | 3316.5
Tables - Unique | Validation | Total | 2.5 | 67 | 167.5 | 5661.5
Tables - Repeat | Creation | Statistician | 0.5 | 23 | 11.5 | 345
Tables - Repeat | Creation | Sr. Statistician | 0 | 23 | 0 | 0
Tables - Repeat | Creation | Stats. Prog. | 2 | 23 | 46 | 1150
Tables - Repeat | Creation | Sr. Stats. Prog. | 0 | 23 | 0 | 0
Tables - Repeat | Creation | Total | 2.5 | 23 | 57.5 | 1495
Tables - Repeat
Tables - Repeat | Validation | Statistician | 0.5 | 23 | 11.5 | 345
Tables - Repeat | Validation | Sr. Statistician | 0 | 23 | 0 | 0
Tables - Repeat | Validation | Stats. Prog. | 0 | 23 | 0 | 0
Tables - Repeat | Validation | Sr. Stats. Prog. | 1 | 23 | 23 | 759
Tables - Repeat | Validation | Total | 1.5 | 23 | 34.5 | 1104
Listings - Unique | Creation | Statistician | 0 | 34 | 0 | 0
Listings - Unique | Creation | Sr. Statistician | 0 | 34 | 0 | 0
Listings - Unique | Creation | Stats. Prog. | 2 | 34 | 68 | 1700
Listings - Unique | Creation | Sr. Stats. Prog. | 0 | 34 | 0 | 0
Listings - Unique | Creation | Total | 2 | 34 | 68 | 1700
Listings - Unique
Listings - Unique | Validation | Statistician | 0.5 | 34 | 17 | 510
Listings - Unique | Validation | Sr. Statistician | 0 | 34 | 0 | 0
Listings - Unique | Validation | Stats. Prog. | 0 | 34 | 0 | 0
Listings - Unique | Validation | Sr. Stats. Prog. | 0.5 | 34 | 17 | 561
Listings - Unique | Validation | Total | 1 | 34 | 34 | 1071
Listings - Repeat | Creation | Statistician | 0 | 11 | 0 | 0
Listings - Repeat | Creation | Sr. Statistician | 0 | 11 | 0 | 0
Listings - Repeat | Creation | Stats. Prog. | 0.5 | 11 | 5.5 | 137.5
Listings - Repeat | Creation | Sr. Stats. Prog. | 0 | 11 | 0 | 0
Listings - Repeat | Creation | Total | 0.5 | 11 | 5.5 | 137.5
Listings - Repeat
Listings - Repeat | Validation | Statistician | 1 | 11 | 11 | 330
Listings - Repeat | Validation | Sr. Statistician | 0 | 11 | 0 | 0
Listings - Repeat | Validation | Stats. Prog. | 0 | 11 | 0 | 0
Listings - Repeat | Validation | Sr. Stats. Prog. | 0.5 | 11 | 5.5 | 181.5
Listings - Repeat | Validation | Total | 1.5 | 11 | 16.5 | 511.5
Figuress - Unique | Creation | Statistician | 1 | 11 | 11 | 330
Figuress - Unique | Creation | Sr. Statistician | 0 | 11 | 0 | 0
Figuress - Unique | Creation | Stats. Prog. | 6 | 11 | 66 | 1650
Figuress - Unique | Creation | Sr. Stats. Prog. | 0 | 11 | 0 | 0
Figuress - Unique | Creation | Total | 7 | 11 | 77 | 1980
Figuress - Unique
Figuress - Unique | Validation | Statistician | 1 | 11 | 11 | 330
Figuress - Unique | Validation | Sr. Statistician | 0.5 | 11 | 5.5 | 220
Figuress - Unique | Validation | Stats. Prog. | 0 | 11 | 0 | 0
Figuress - Unique | Validation | Sr. Stats. Prog. | 1.5 | 11 | 16.5 | 544.5
Figuress - Unique | Validation | Total | 3 | 11 | 33 | 1094.5
Figures - Repeat | Creation | Statistician | 0 | 4 | 0 | 0
Figures - Repeat | Creation | Sr. Statistician | 0 | 4 | 0 | 0
Figures - Repeat | Creation | Stats. Prog. | 1 | 4 | 4 | 100
Figures - Repeat | Creation | Sr. Stats. Prog. | 0 | 4 | 0 | 0
Figures - Repeat | Creation | Total | 1 | 4 | 4 | 100
Figures - Repeat
Figures - Repeat | Validation | Statistician | 0.5 | 4 | 2 | 60
Figures - Repeat | Validation | Sr. Statistician | 0 | 4 | 0 | 0
Figures - Repeat | Validation | Stats. Prog. | 0 | 4 | 0 | 0
Figures - Repeat | Validation | Sr. Stats. Prog. | 0.5 | 4 | 2 | 66
Figures - Repeat | Validation | Total | 1 | 4 | 4 | 126
Tables - Intext | Creation | Statistician | 0.5 | 12 | 6 | 180
Tables - Intext | Creation | Sr. Statistician | 0 | 12 | 0 | 0
Tables - Intext | Creation | Stats. Prog. | 4 | 12 | 48 | 1200
Tables - Intext | Creation | Sr. Stats. Prog. | 0 | 12 | 0 | 0
Tables - Intext | Creation | Total | 4.5 | 12 | 54 | 1380
Tables - Intext
Tables - Intext | Validation | Statistician | 0.5 | 12 | 6 | 180
Tables - Intext | Validation | Sr. Statistician | 0.5 | 12 | 6 | 240
Tables - Intext | Validation | Stats. Prog. | 0 | 12 | 0 | 0
Tables - Intext | Validation | Sr. Stats. Prog. | 1.5 | 12 | 18 | 594
Tables - Intext | Validation | Total | 2.5 | 12 | 30 | 1014
Listings - Intext | Creation | Statistician | 1 | 6 | 6 | 180 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Creation | Sr. Statistician | 0 | 6 | 0 | 0
Listings - Intext | Creation | Stats. Prog. | 0.5 | 6 | 3 | 75
Listings - Intext | Creation | Sr. Stats. Prog. | 0 | 6 | 0 | 0
Listings - Intext | Creation | Total | 1.5 | 6 | 9 | 255
Listings - Intext
Listings - Intext | Validation | Statistician | 1 | 6 | 6 | 180 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Validation | Sr. Statistician | 1 | 6 | 6 | 240 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Validation | Stats. Prog. | 0 | 6 | 0 | 0
Listings - Intext | Validation | Sr. Stats. Prog. | 0.5 | 6 | 3 | 99
Listings - Intext | Validation | Total | 2.5 | 6 | 15 | 519
Figures - Intext | Creation | Statistician | 1 | 2 | 2 | 60
Figures - Intext | Creation | Sr. Statistician | 0 | 2 | 0 | 0
Figures - Intext | Creation | Stats. Prog. | 6 | 2 | 12 | 300
Figures - Intext | Creation | Sr. Stats. Prog. | 0 | 2 | 0 | 0
Figures - Intext | Creation | Total | 7 | 2 | 14 | 360
Figures - Intext
Figures - Intext | Validation | Statistician | 1 | 2 | 2 | 60
Figures - Intext | Validation | Sr. Statistician | 0.5 | 2 | 1 | 40
Figures - Intext | Validation | Stats. Prog. | 0 | 2 | 0 | 0
Figures - Intext | Validation | Sr. Stats. Prog. | 1.5 | 2 | 3 | 99
Figures - Intext | Validation | Total | 3 | 2 | 6 | 199
Total | Creation | Statistician |  |  | 81 | 2430
Total | Creation | Sr. Statistician |  |  | 0 | 0
Total | Creation | Stats. Prog. |  |  | 657.5 | 16437.5
Total | Creation | Sr. Stats. Prog. |  |  | 0 | 0
Total | Creation | Total |  |  | 738.5 | 18867.5
Total |  | Total Check |  |  | 738.5 | 18867.5
Total | Validation | Statistician |  |  | 111 | 3330
Total | Validation | Sr. Statistician |  |  | 64 | 2560
Total | Validation | Stats. Prog. |  |  | 0 | 0
Total | Validation | Sr. Stats. Prog. |  |  | 464.5 | 15328.5
Total | Validation | Total |  |  | 639.5 | 21218.5
Total |  | Total Check |  |  | 639.5 | 21218.5
Grand Total | C&V | Statistician |  |  | 192 | 5760 | 288 |  | 96
Grand Total | C&V | Sr. Statistician |  |  | 64 | 2560 | 96 |  | 32
Grand Total | C&V | Stats. Prog. |  |  | 657.5 | 16437.5 | 986.25 |  | 328.75
Grand Total | C&V | Sr. Stats. Prog. |  |  | 464.5 | 15328.5 | 696.75 |  | 232.25
Grand Total | C&V | Total |  |  | 1378 | 40086 | 2067 |  | 689
Grand Total | C&V | Total Check |  |  | 1378 | 40086 | 2067 |  | 689
[5 empty] | TLF |  | ADaM
|  | Statistician |  |  | 142 |  | 50
|  | Sr. Statistician |  |  | 39 |  | 25
|  | Stats. Prog. |  |  | 457.5 |  | 200
|  | Sr. Stats. Prog. |  |  | 164.5 |  | 300
Total

## High
|  |  |  | Multiplier for unit for SAP |  |  | 1.8148
Activity | Sub Activity | Role | Hours / Unit | No. of Units | Efforts | Cost
SAP and Mock shells | Creation | Statistician | 64 | 1 | 116 | 3480
SAP and Mock shells | Creation | Sr. Statistician | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Stats. Prog. | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Sr. Stats. Prog. | 0 | 1 | 0 | 0
SAP and Mock shells | Creation | Total | 64 | 1 | 116 | 3480
SAP and Mock shells
SAP and Mock shells | Review | Statistician | 1 | 1 | 2 | 60
SAP and Mock shells | Review | Sr. Statistician | 12 | 1 | 22 | 880
SAP and Mock shells | Review | Stats. Prog. | 25 | 1 | 45 | 1125
SAP and Mock shells | Review | Sr. Stats. Prog. | 14 | 1 | 25 | 825
SAP and Mock shells | Review | Total | 52 | 1 | 94 | 2890
SDTM | Creation | Statistician | 0 | 40 | 0 | 0
SDTM | Creation | Sr. Statistician | 0 | 40 | 0 | 0
SDTM | Creation | Stats. Prog. | 6 | 40 | 240 | 6000
SDTM | Creation | Sr. Stats. Prog. | 0 | 40 | 0 | 0
SDTM | Creation | Total | 6 | 40 | 240 | 6000
SDTM
SDTM | Validation | Statistician | 3.2 | 40 | 128 | 3840
SDTM | Validation | Sr. Statistician | 1.2 | 40 | 48 | 1920
SDTM | Validation | Stats. Prog. | 0 | 40 | 0 | 0
SDTM | Validation | Sr. Stats. Prog. | 4 | 40 | 160 | 5280
SDTM | Validation | Total | 8.4 | 40 | 336 | 11040
ADaM | Creation | Statistician | 1 | 30 | 30 | 900
ADaM | Creation | Sr. Statistician | 0 | 30 | 0 | 0
ADaM | Creation | Stats. Prog. | 8 | 30 | 240 | 6000
ADaM | Creation | Sr. Stats. Prog. | 0 | 30 | 0 | 0
ADaM | Creation | Total | 9 | 30 | 270 | 6900
ADaM
ADaM | Validation | Statistician | 1 | 30 | 30 | 900
ADaM | Validation | Sr. Statistician | 1 | 30 | 30 | 1200
ADaM | Validation | Stats. Prog. | 0 | 30 | 0 | 0
ADaM | Validation | Sr. Stats. Prog. | 12 | 30 | 360 | 11880
ADaM | Validation | Total | 14 | 30 | 420 | 13980
Tables - Unique | Creation | Statistician | 0.5 | 89 | 44.5 | 1335
Tables - Unique | Creation | Sr. Statistician | 0 | 89 | 0 | 0
Tables - Unique | Creation | Stats. Prog. | 4 | 89 | 356 | 8900
Tables - Unique | Creation | Sr. Stats. Prog. | 0 | 89 | 0 | 0
Tables - Unique | Creation | Total | 4.5 | 89 | 400.5 | 10235
Tables - Unique
Tables - Unique | Validation | Statistician | 0.5 | 89 | 44.5 | 1335
Tables - Unique | Validation | Sr. Statistician | 0.5 | 89 | 44.5 | 1780
Tables - Unique | Validation | Stats. Prog. | 0 | 89 | 0 | 0
Tables - Unique | Validation | Sr. Stats. Prog. | 1.5 | 89 | 133.5 | 4405.5
Tables - Unique | Validation | Total | 2.5 | 89 | 222.5 | 7520.5
Tables - Repeat | Creation | Statistician | 0.5 | 16 | 8 | 240
Tables - Repeat | Creation | Sr. Statistician | 0 | 16 | 0 | 0
Tables - Repeat | Creation | Stats. Prog. | 2 | 16 | 32 | 800
Tables - Repeat | Creation | Sr. Stats. Prog. | 0 | 16 | 0 | 0
Tables - Repeat | Creation | Total | 2.5 | 16 | 40 | 1040
Tables - Repeat
Tables - Repeat | Validation | Statistician | 0.5 | 16 | 8 | 240
Tables - Repeat | Validation | Sr. Statistician | 0 | 16 | 0 | 0
Tables - Repeat | Validation | Stats. Prog. | 0 | 16 | 0 | 0
Tables - Repeat | Validation | Sr. Stats. Prog. | 1 | 16 | 16 | 528
Tables - Repeat | Validation | Total | 1.5 | 16 | 24 | 768
Listings - Unique | Creation | Statistician | 0 | 44.5 | 0 | 0
Listings - Unique | Creation | Sr. Statistician | 0 | 44.5 | 0 | 0
Listings - Unique | Creation | Stats. Prog. | 2 | 44.5 | 89 | 2225
Listings - Unique | Creation | Sr. Stats. Prog. | 0 | 44.5 | 0 | 0
Listings - Unique | Creation | Total | 2 | 44.5 | 89 | 2225
Listings - Unique
Listings - Unique | Validation | Statistician | 0.5 | 44.5 | 22.25 | 667.5
Listings - Unique | Validation | Sr. Statistician | 0 | 44.5 | 0 | 0
Listings - Unique | Validation | Stats. Prog. | 0 | 44.5 | 0 | 0
Listings - Unique | Validation | Sr. Stats. Prog. | 0.5 | 44.5 | 22.25 | 734.25
Listings - Unique | Validation | Total | 1 | 44.5 | 44.5 | 1401.75
Listings - Repeat | Creation | Statistician | 0 | 8 | 0 | 0
Listings - Repeat | Creation | Sr. Statistician | 0 | 8 | 0 | 0
Listings - Repeat | Creation | Stats. Prog. | 0.5 | 8 | 4 | 100
Listings - Repeat | Creation | Sr. Stats. Prog. | 0 | 8 | 0 | 0
Listings - Repeat | Creation | Total | 0.5 | 8 | 4 | 100
Listings - Repeat
Listings - Repeat | Validation | Statistician | 1 | 8 | 8 | 240
Listings - Repeat | Validation | Sr. Statistician | 0 | 8 | 0 | 0
Listings - Repeat | Validation | Stats. Prog. | 0 | 8 | 0 | 0
Listings - Repeat | Validation | Sr. Stats. Prog. | 0.5 | 8 | 4 | 132
Listings - Repeat | Validation | Total | 1.5 | 8 | 12 | 372
Figuress - Unique | Creation | Statistician | 1 | 14.5 | 14.5 | 435
Figuress - Unique | Creation | Sr. Statistician | 0 | 14.5 | 0 | 0
Figuress - Unique | Creation | Stats. Prog. | 6 | 14.5 | 87 | 2175
Figuress - Unique | Creation | Sr. Stats. Prog. | 0 | 14.5 | 0 | 0
Figuress - Unique | Creation | Total | 7 | 14.5 | 101.5 | 2610
Figuress - Unique
Figuress - Unique | Validation | Statistician | 1 | 14.5 | 14.5 | 435
Figuress - Unique | Validation | Sr. Statistician | 0.5 | 14.5 | 7.25 | 290
Figuress - Unique | Validation | Stats. Prog. | 0 | 14.5 | 0 | 0
Figuress - Unique | Validation | Sr. Stats. Prog. | 1.5 | 14.5 | 21.75 | 717.75
Figuress - Unique | Validation | Total | 3 | 14.5 | 43.5 | 1442.75
Figures - Repeat | Creation | Statistician | 0 | 3 | 0 | 0
Figures - Repeat | Creation | Sr. Statistician | 0 | 3 | 0 | 0
Figures - Repeat | Creation | Stats. Prog. | 1 | 3 | 3 | 75
Figures - Repeat | Creation | Sr. Stats. Prog. | 0 | 3 | 0 | 0
Figures - Repeat | Creation | Total | 1 | 3 | 3 | 75
Figures - Repeat
Figures - Repeat | Validation | Statistician | 0.5 | 3 | 1.5 | 45
Figures - Repeat | Validation | Sr. Statistician | 0 | 3 | 0 | 0
Figures - Repeat | Validation | Stats. Prog. | 0 | 3 | 0 | 0
Figures - Repeat | Validation | Sr. Stats. Prog. | 0.5 | 3 | 1.5 | 49.5
Figures - Repeat | Validation | Total | 1 | 3 | 3 | 94.5
Tables - Intext | Creation | Statistician | 0.5 | 18 | 9 | 270
Tables - Intext | Creation | Sr. Statistician | 0 | 18 | 0 | 0
Tables - Intext | Creation | Stats. Prog. | 4 | 18 | 72 | 1800
Tables - Intext | Creation | Sr. Stats. Prog. | 0 | 18 | 0 | 0
Tables - Intext | Creation | Total | 4.5 | 18 | 81 | 2070
Tables - Intext
Tables - Intext | Validation | Statistician | 0.5 | 18 | 9 | 270
Tables - Intext | Validation | Sr. Statistician | 0.5 | 18 | 9 | 360
Tables - Intext | Validation | Stats. Prog. | 0 | 18 | 0 | 0
Tables - Intext | Validation | Sr. Stats. Prog. | 1.5 | 18 | 27 | 891
Tables - Intext | Validation | Total | 2.5 | 18 | 45 | 1521
Listings - Intext | Creation | Statistician | 1 | 9 | 9 | 270 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Creation | Sr. Statistician | 0 | 9 | 0 | 0
Listings - Intext | Creation | Stats. Prog. | 0.5 | 9 | 4.5 | 112.5
Listings - Intext | Creation | Sr. Stats. Prog. | 0 | 9 | 0 | 0
Listings - Intext | Creation | Total | 1.5 | 9 | 13.5 | 382.5
Listings - Intext
Listings - Intext | Validation | Statistician | 1 | 9 | 9 | 270 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Validation | Sr. Statistician | 1 | 9 | 9 | 360 |  | To accommodate Medical Review efforts are added here
Listings - Intext | Validation | Stats. Prog. | 0 | 9 | 0 | 0
Listings - Intext | Validation | Sr. Stats. Prog. | 0.5 | 9 | 4.5 | 148.5
Listings - Intext | Validation | Total | 2.5 | 9 | 22.5 | 778.5
Figures - Intext | Creation | Statistician | 1 | 3 | 3 | 90
Figures - Intext | Creation | Sr. Statistician | 0 | 3 | 0 | 0
Figures - Intext | Creation | Stats. Prog. | 6 | 3 | 18 | 450
Figures - Intext | Creation | Sr. Stats. Prog. | 0 | 3 | 0 | 0
Figures - Intext | Creation | Total | 7 | 3 | 21 | 540
Figures - Intext
Figures - Intext | Validation | Statistician | 1 | 3 | 3 | 90
Figures - Intext | Validation | Sr. Statistician | 0.5 | 3 | 1.5 | 60
Figures - Intext | Validation | Stats. Prog. | 0 | 3 | 0 | 0
Figures - Intext | Validation | Sr. Stats. Prog. | 1.5 | 3 | 4.5 | 148.5
Figures - Intext | Validation | Total | 3 | 3 | 9 | 298.5
Total | Creation | Statistician |  |  | 97 | 2910
Total | Creation | Sr. Statistician |  |  | 0 | 0
Total | Creation | Stats. Prog. |  |  | 811 | 20275
Total | Creation | Sr. Stats. Prog. |  |  | 0 | 0
Total | Creation | Total |  |  | 908 | 23185
Total |  | Total Check |  |  | 908 | 23185
Total | Validation | Statistician |  |  | 128.75 | 3862.5
Total | Validation | Sr. Statistician |  |  | 81.75 | 3270
Total | Validation | Stats. Prog. |  |  | 0 | 0
Total | Validation | Sr. Stats. Prog. |  |  | 559 | 18447
Total | Validation | Total |  |  | 769.5 | 25579.5
Total |  | Total Check |  |  | 769.5 | 25579.5
Grand Total | C&V | Statistician |  |  | 225.75 | 6772.5 | 338.625 |  | 112.875
Grand Total | C&V | Sr. Statistician |  |  | 81.75 | 3270 | 122.625 |  | 40.875
Grand Total | C&V | Stats. Prog. |  |  | 811 | 20275 | 1216.5 |  | 405.5
Grand Total | C&V | Sr. Stats. Prog. |  |  | 559 | 18447 | 838.5 |  | 279.5
Grand Total | C&V | Total |  |  | 1677.5 | 48764.5 | 2516.25 |  | 838.75
Grand Total | C&V | Total Check |  |  | 1677.5 | 48764.5 | 2516.25 |  | 838.75
[5 empty] | TLF |  | ADaM
|  | Statistician |  |  | 165.75 |  | 60
|  | Sr. Statistician |  |  | 51.75 |  | 30
|  | Stats. Prog. |  |  | 571 |  | 240
|  | Sr. Stats. Prog. |  |  | 199 |  | 360
Total

## e-sub
Activity | Sub Activity | Role | Low complexity |  |  | Medium complexity |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost | Efforts in hours | Efforts in days | Cost | Efforts in hours | Efforts in days | Cost
SDTM eSub Package | C&V | Statistician | 2.4 | 0.3 | 72 | 3 | 0.375 | 90 | 3.75 | 0.46875 | 112.5
SDTM eSub Package | C&V | Sr. Statistician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SDTM eSub Package | C&V | Stats. Prog. | 128 | 16 | 3200 | 160 | 20 | 4000 | 200 | 25 | 5000
SDTM eSub Package | C&V | Sr. Stats. Prog. | 64 | 8 | 2112 | 80 | 10 | 2640 | 100 | 12.5 | 3300
SDTM eSub Package | C&V | Total | 194.4 | 24.3 | 5384 | 243 | 30.375 | 6730 | 303.75 | 37.9688 | 8412.5
Activity | Sub Activity | Role | Low complexity |  |  | Medium complexity |  |  | High complexity
|  |  | Efforts in hours | Efforts in days | Cost | Efforts in hours | Efforts in days | Cost | Efforts in hours | Efforts in days | Cost
ADaM eSub Package | C&V | Statistician | 8 | 1 | 240 | 10 | 1.25 | 300 | 12.5 | 1.5625 | 375
ADaM eSub Package | C&V | Sr. Statistician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADaM eSub Package | C&V | Stats. Prog. | 92.8 | 11.6 | 2320 | 116 | 14.5 | 2900 | 145 | 18.125 | 3625
ADaM eSub Package | C&V | Sr. Stats. Prog. | 49.6 | 6.2 | 1636.8 | 62 | 7.75 | 2046 | 77.5 | 9.6875 | 2557.5
ADaM eSub Package | C&V | Total | 150.4 | 18.8 | 4196.8 | 188 | 23.5 | 5246 | 235 | 29.375 | 6557.5