## Slide 1: Milestones of Clinical trial & Clinical Study Report
Release Date: DD-Mmm-YYYY

## Slide 2: Milestones of clinical trial
Clinical trials are research studies involving human population (healthy volunteers known as subjects / diseased population known as patients) to evaluate or explore whether the new intervention or treatment , strategy or devise is safe and effective for humans.
Clinical trial comprises of various stages, in this presentation we focus on stages related to biostatistics and programming:
Planning
Execution
Reporting

## Slide 3: Planning stage of Clinical Trial
Clinical Development Plan (CDP)
Protocol Development
CRF setup
Database development
Data Handling Plan (DHP)
Data Validation Plan
Statistical Analysis Plan
  Statistical Methodology
  Mock shells
  Analysis dataset specifications
Investigator Brochure or equivalent document for study intervention

## Slide 4: Execution stage of Clinical Trial
Execution phase has various milestone
  First Patient First Visit (FPFV)
  First Data Generated (FDG)
  Blinded interim data review for cleaning and monitoring
  Programming Dry-run
    Setup programs for Value Added Datasets / Analysis Datasets
    Setup programs for Tables Listings and Figures
    Validation
    Testing of programs for correctness and meeting the SAP requirement
  Last Data Generated (LDG)
  Complete Data Check (CDC)
  Database Lock (DBL)

## Slide 5: Reporting stage of Clinical Trial
Opening of the blind and checking of the randomization scheme
Final execution of the programs for generation of VAD and TFLs on the un-blinded DB.
Release of the Key (decision making) reports to the management team with in 5 working days of the DBL. In case of fast track or breakthrough trials, these can be released to the HA’s as well
Final release of all the outputs to the medical write for the development of Clinical Study Report (CSR)
Generation of Study Data Reviewer’s Guide
Generation of Analysis Data Reviewer’s Guide
Creation of Annotated CRF
Generation of Define.xml
Archival of the final deliverables

## Slide 6: Clinical Study Report (CSR)
A detailed summary of the clinical trial summarizing the details of the conduct of the clinical trial along with the conclusion and interpretation derived out of the results produced is known as a Clinical Study Report (CSR).
CSR is a scientific document summarizing the safety and efficacy of the drug of interest.
CSR is a mandatory document for any HA submission.
The ICH E3 guideline defines the structure template for the CSR
There are two types of CSR:
  Full CSR
  Abbreviated CSR (only for discontinued / terminated trials)

## Slide 7
Thank You!
For any feedback/comment/clarification please contact us at PALS@tcs.com
Copyright © 2012 Tata Consultancy Services Limited
V 00.00

## Slide 8: Change/Revision History
Revision Description | Slide No. | Rationale for the Change | Change type (Add/Modify/Delete) | Modified By | Date Modified (DD-Mmm-YYYY)
Initial Release | NA | NA | NA | NA | Na