## Sheet1
Biostatistics and Statistical Programming delivery for <XXX> client
|  | SL, SP, SS and rest of the team |  | Created by Stats. Review by SL, SS and SP.
|  | Process trainings (Client / TCS internal) |  | Creation of SAP and Mock shells
|  | Internet access, WebEx, Learn Account,etc |  | Created in excel provided in the server and stored in DOC/OTHERS
|  | 1 weeks |  | 2-4 weeks
| SL, SP, SS and rest of the team | SL in accordance with SP and SS | Client provided | Created by Stats/Programmer. Review by SL, SS and SP. | Programmer
| Kick off meeting | Scope identification Timeline negotiation | Receipt of all study level documentation and validation plan | Creation of programming specifications | Programming for Analysis datasets and TFL creation
| WebEx access and account required | Open office/ WebEx | Open office/ WebEx/ Citrix/ CSA access in Wise | Created in excel provided in the server and stored in DOC/OTHERS | Working on SAS EG with all macro(like G-Star, SuSads), dictionaries and CSA accesses. Need to keep SAP, Protocol, Specification, CRF, IG etc. handy.
| 1 day | 1 weeks | Follow up required- max 1 week | 2-4 weeks | 2-4 months
|  | SL, SP, SS and rest of the team |  | SL to create QC and tracking document.
|  | Account / Portal access |  | Creation of QC and tracking sheet
|  | Internet access, training completion certificates, Wise access |  | Open Office
|  | 1/2 weeks |  | 1-2 days
Rerunning by TCS-programmer and reviewing by TCS-Stats/SS/SP
Each data snapshot re-run and review by TCS internal team
Tools like Ultra-compare used.
2-4 days
| SS/SP to perform critical review in confirmation with SL. SL to release package. | TCS-programmer to update/modify. Stats to review. | TCS-programmer to update/modify as per comment and reviewing by TCS-Stats Final review by SP/SS/SL | Review by SL, SS and SP. | TCS programmer to validate, SP to review. Stats/SS for critical review and consistence with Specs and Mock-shell
| Final review from TCS internal and released for client acknowledgement | Re-run at final DBL and ensuring all comments are addressed | Client comments addressed and acknowledgment receipt | Intermediate submission (Dryrun) as per agreed timeline | Validation and review of Analysis datasets and TFLS
| Done in SAS and Ultra-compare and data-set review. | Done in SAS and Ultra-compare and data-set review. | Comments are usually provided in Comments tracker places in DOC/OTHERS | Package prepared in collated formats like GS-packs | Working on SAS EG with all macro(like G-Star, SuSads), dictionaries and CSA accesses. Need to keep SAP, Protocol, Specification, CRF, IG etc. handy. Also, need knowledge of client applications like Ultra compare to ease the process.
| 1-2 days | 1-2 weeks | 2-5 days | 1-2 days | 1-2 months
| TCS-programmer and reviewing by TCS-Stats. Finalization by SS/SP/SL. Final mail to be communicated by SL. | Activity is carried out by TCS-programmer and reviewed by TCS-Stats. Critical review by SS/SP/SL. Final review by client. | TCS programmer and cross-checked by SP. | Stats and cross-verified by SS. All activity acknowledged by SL and client.
| Fixing client comments and finalizing the package in approval of the client | Creation of production package post client approval | Close out activity of Log checks, archival of codes and deliverables in appropriate locations | Finalization of the trackers and all required documentation and final sign-off
| Done in SAS and Ultra-compare and data-set review. | All required program/document are copied from Development to Production area and re-run. All data-sets, outputs are then compared with the finalized data in Development area. Done in SAS and Ultra-compare and data-set review. | Done in SAS and Wise | Created in excel/words provided in the server and stored in DOC/OTHERS
| 2-5 days | 1-2 days | 1 days | 1-4 days